## Sheet1
source_table | labor_SNo | labor_Type | labor_Count | labor_Remarks | machinery_SNo | machinery_Discription | machinery_Number | machinery_Working | machinery_Out_of_order | machinery_Remarks | material_SNo | material_Item | material_Unit | material_Last | material_Received | material_Utilized | material_Remaining | money_SNo | money_Name_of_Vendor | money_Type_of_work | money_Price | money_Payment | money_Transaction_amt | money_Balance | money_bill | progress_SNo | progress_Activity | progress_Unit | progress_Total_Qty | progress_Executed_Qty | progress_Remarks
labor | 1 | Mason | 5
labor | 2 | Carpenter | 3
labor | 3 | SteelFixer | 4
labor | 4 | Labor | 10
labor | 5 | Electrician | 2
labor | 6 | Plumber | 2
labor | 7 | Foreman | 1
labor | 10 | bender | 3
labor | 11 | carpentor | 10
labor | 12 | bender | 4 | working too slow
machinery |  |  |  |  | 1 | Excavator | 2 | 2 | 0
machinery |  |  |  |  | 2 | Concrete Mixer | 3 | 2 | 0 | 1 machine under repair
machinery |  |  |  |  | 3 | Crane | 1 | 1 | 0
machinery |  |  |  |  | 4 | Bulldozer | 2 | 1 | 1 | 1 machine idle
machinery |  |  |  |  | 5 | Generator | 2 | 2 | 0
machinery |  |  |  |  | 6 | Welding Machine | 4 | 3 | 1 | 1 idle for maintenance
machinery |  |  |  |  | 7 | Vibrator | 3 | 2 | 0 | 1 idle
machinery |  |  |  |  | 10 | Vibrator | 4 | 3 | 1 | 1 idle because repair
machinery |  |  |  |  | 11 | welding machine | 3 | 2 | 1 | repair
material | [10 empty] | 1 | Cement | bags | 50 | 100 | 80 | 70
material | [10 empty] | 2 | Sand | mÂ³ | 200 | 150 | 180 | 170
material | [10 empty] | 3 | Steel Rods | kg | 100 | 50 | 60 | 90
material | [10 empty] | 4 | Bricks | nos | 500 | 300 | 400 | 400
material | [10 empty] | 5 | Gravel | mÂ³ | 150 | 100 | 80 | 170
material | [10 empty] | 6 | Tiles | sq.m | 200 | 50 | 70 | 180
material | [10 empty] | 7 | Paint | liters | 30 | 20 | 25 | 25
material | [10 empty] | 10 | Paint | liters | 40 | 20 | 50 | 10
money | [17 empty] | 1 | surya | ceiling | 5000 | 3000 | 3000 | 2000
money | [17 empty] | 2 | lokesh | flooring | 8000 | 5000 | 5000 | 3000 | ÿØÿà
progress | [25 empty] | 1 | Excavation of foundation | mÂ³ | 120 | 50
progress | [25 empty] | 2 | Concrete pouring | mÂ³ | 80 | 30
progress | [25 empty] | 3 | Brick wall construction | nos | 200 | 90
progress | [25 empty] | 4 | Plastering walls | sq.m | 150 | 60
progress | [25 empty] | 5 | Flooring installation | sq.m | 100 | 25
progress | [25 empty] | 6 | chinnu | amps | 600 | 455 | my name is arunkumar and iam backend engineer
progress | [25 empty] | 10 | wall plasting | sq.m | 130 | 100 | ciment not ok